## 📊 Dashboard
AI-Powered Stateful Firewall - Project Tracker
Last Updated: 2026-06-26 02:04
PROJECT STATUS
Overall Progress: | Phase 2C | 30% (Start)
Phases Complete: | 1-2B | 100%
Current Phase: | 2C (Dashboard) | In Progress
Phase 2D (ML): | Pending | Not Started
PROJECT TIMELINE
Phase | Duration | Status
Phase 2C (Dashboard) | 3-4 weeks | In Progress
Phase 2D (ML) | 2-3 weeks | Pending
Phase 2E (Performance) | 1 week | Pending
Phase 2F (Docs) | 1 week | Pending
KEY METRICS
Total Tasks Phase 2C+2D: | 38 tasks
Completed: | 0 tasks
In Progress: | 1 task
Pending: | 37 tasks

## 📋 Task List
Task Name | Phase | Category | Assigned To | Status | Est. Hrs | Act. Hrs | Notes
Project setup + React + TypeScript | 2C | Setup | Agent | In Progress | 3 | 0 | Vite, TypeScript config
Login/Auth page | 2C | Frontend | Agent | Pending | 2 | 0 | API key auth
Page 1: Live Dashboard (stats) | 2C | Frontend | Agent | Pending | 5 | 0 | Stat cards, real-time
Page 1: Alert feed | 2C | Frontend | Agent | Pending | 4 | 0 | Scrolling alerts
Page 1: Protocol chart | 2C | Frontend | Agent | Pending | 3 | 0 | Recharts
WebSocket integration | 2C | Frontend | Agent | Pending | 4 | 0 | Real-time hook
Page 2: Connections table | 2C | Frontend | Agent | Pending | 6 | 0 | Sortable, filterable
Page 3: Alerts history | 2C | Frontend | Agent | Pending | 5 | 0 | Filter by severity
Page 4: Rules manager | 2C | Frontend | Agent | Pending | 6 | 0 | CRUD operations
Page 5: Analytics | 2C | Frontend | Agent | Pending | 5 | 0 | Charts, trends
API integration | 2C | Integration | Agent | Pending | 4 | 0 | TanStack Query
Styling + Dark theme | 2C | Styling | Agent | Pending | 6 | 0 | Tailwind, responsive
Testing + Bug fixes | 2C | QA | Agent | Pending | 5 | 0 | Cross-browser
Demo video | 2C | Deliverable | Aakash | Pending | 2 | 0 | Screen recording
Feature extraction review | 2D | ML | Agent | Pending | 2 | 0 | Review code
Baseline data collection | 2D | ML | Agent | Pending | 3 | 0 | 24h+ normal traffic
Feature engineering (11 features) | 2D | ML | Agent | Pending | 4 | 0 | Extract metrics
Isolation Forest training | 2D | ML | Agent | Pending | 4 | 0 | Train + eval
Anomaly detector inference | 2D | ML | Agent | Pending | 3 | 0 | Real-time predict
ML pipeline integration | 2D | Integration | Agent | Pending | 4 | 0 | 5-min windows
Threat score combining | 2D | ML | Agent | Pending | 3 | 0 | Heuristic + ML + TI
ML alerts on dashboard | 2D | Frontend | Agent | Pending | 3 | 0 | Display scores
Model persistence | 2D | ML | Agent | Pending | 2 | 0 | Save/load pkl
Training docs | 2D | Documentation | Agent | Pending | 2 | 0 | Retrain guide
Port Scan test (Nmap) | Validation | Testing | Aakash | Pending | 1 | 0 | Check detection
SYN Flood test (hping3) | Validation | Testing | Aakash | Pending | 1 | 0 | Check detection
ICMP Flood test (ping) | Validation | Testing | Aakash | Pending | 1 | 0 | Check detection
Performance testing | Validation | Testing | Agent | Pending | 2 | 0 | Load test
DB optimization | Optimization | Backend | Agent | Pending | 2 | 0 | Add indexes
HTTPS setup | Optimization | Security | Agent | Pending | 2 | 0 | Self-signed cert
Final demo video | Deliverable | Deliverable | Aakash | Pending | 3 | 0 | 5-min demo

## 📅 Timeline
Phase 2C Timeline (June 26 - July 17, 2026)
Week 1: React Setup + Page 1
• Project setup (Vite, TypeScript)
• Login/Auth
• Page 1: Live Dashboard (stats, alert feed, chart)
• WebSocket integration
Week 2: Pages 2-3 + API Integration
• Page 2: Active Connections (sortable table)
• Page 3: Alerts history
• API integration (fetch calls)
Week 3: Pages 4-5 + Styling
• Page 4: Firewall Rules manager
• Page 5: Analytics & Reports
• Styling (dark theme, responsive)
Week 4: Testing + Demo
• Testing & bug fixes
• Demo video recording
Phase 2D Timeline (July 18 - Aug 7, 2026)
Week 1: ML Setup + Data Collection
• Baseline data collection (24h+)
• Feature extraction
• Isolation Forest training
Week 2: ML Integration + Testing
• Anomaly detector inference
• ML pipeline integration
• Threat score combining
• Dashboard ML alerts

## 📝 Daily Log
Date | Work Done | Hrs | Person
Template:
YYYY-MM-DD | Describe work completed | 0 | Agent/Aakash

## 🤖 Agent Work
Date | Task Completed | Category | Hrs | Notes/Link
Template:
YYYY-MM-DD | Task name | Frontend/ML/etc | 0 | GitHub PR link or notes

## ⚠️ Risks
Risk | Likelihood | Impact | Mitigation | Status
WebSocket flakiness | Medium | High | Implement polling fallback | Active
ML model fails | Low | High | Start data early; keep heuristic backup | Active
React complexity | Medium | Medium | Fallback to Streamlit | Active
Database locks on load | Medium | Medium | Add indexes; prepare PostgreSQL plan | Active
Scope creep | High | High | Cut rules management if needed | Active
Time overrun | High | High | Ruthless scope management | Active

## 🔗 Dependencies
Task | Depends On | Status
Page 1: Live Dashboard | React + TypeScript setup | Pending
Page 1: Alert feed | WebSocket integration | Pending
WebSocket integration | API backend (DONE) | Ready
All Pages (2-5) | API integration setup | Pending
Styling + Responsive | All pages created | Pending
ML integration | Feature extraction (DONE) | Ready
Anomaly detector | Baseline data collection | Pending
ML alerts on dashboard | Anomaly detector DONE | Pending
Phase 2D start | Phase 2C DONE | Pending

## 👥 Resources
Team | Role | Hrs/Week | Focus Areas
Aakash | Project Lead | 20-25 | Attack tests, demo, reviews
Claude (Agent) | Developer | 40+ | Frontend coding, ML, integration

## 📌 Notes
Project Notes & Changelog
Key Decisions:
✓ Frontend: React + TypeScript (not Streamlit) - more interview-impressive
✓ ML Algorithm: Isolation Forest - fast inference, unsupervised
✓ Dashboard: 5 pages (stats, connections, alerts, rules, analytics)
✓ Deployment: Docker + self-signed HTTPS
Important Dates:
Phase 2C Start: 2026-06-26
Phase 2C End: 2026-07-17 (3 weeks)
Phase 2D Start: 2026-07-18
Phase 2D End: 2026-08-07 (2 weeks)
Final Demo Ready: 2026-08-22
Success Criteria:
□ Dashboard displays live traffic, connections, alerts
□ WebSocket real-time updates working
□ Firewall detects real attacks (Nmap, hping3, ping)
□ ML model trained and integrated
□ Combined threat scoring (heuristic + ML)
□ 5-minute demo video ready
□ All tests passing
Current Status:
Phases 1-2B: 100% COMPLETE
Phase 2C: 0% - Starting React setup
Phase 2D: 0% - Will start after Phase 2C